## Slide 1
PROJECT PLAN · OCTOBER 2026
Lion's Mane Cultivation & Processing Facility
Commercial production of Hericium erinaceus fruiting-body powder for nutraceutical, Ayurveda and nootropic brands
Hamirpur, Himachal Pradesh, India
Fruiting-body only
Lot-wise NABL CoA
Unidirectional biosecure design
Notes: Opening: this deck covers the biology, facility design, processing, quality, market, economics, regulatory path and implementation plan for a Lion's Mane (Hericium erinaceus) facility at Hamirpur, HP.

## Slide 2
EXECUTIVE SUMMARY
A phased, lab-grade Lion's Mane plant in the Himalayan foothills
Lion's Mane Facility · Hamirpur, HP · Project Plan
2
60 → 90
fruiting blocks inoculated per day
(Phase 1 → Phase 2)
3.6 → 5.4 kg
dry fruiting-body powder per operating day (base case, 65% BE)
₹18.85 L
total Phase-1 project cost incl. ₹4 L working capital
~13 months
EBITDA payback from project start (Phase 1, ₹8,000/kg)
The plan in brief
Grow Lion's Mane on "Master's Mix" (hardwood + soy hull) in a sterile, unidirectional facility: dirty → clean → spore-wet.
Sell tested, fruiting-body-only dried powder to nutraceutical, Ayurveda and nootropic brands at ₹8,000–12,000/kg (B2B).
Phase 1: 60 blocks/day in a tightly zoned 750 sq ft plant. Phase 2: 90 blocks/day to deliver the 5 kg/day target reliably.
Cash cost ~₹3,000/kg vs. ₹8,000/kg base price; break-even at ~37% of Phase-1 output.
Funding led by PMEGP (35% margin-money subsidy, 5% promoter share) with MIDH/NHB and PMFME as alternates.
First harvest ~Month 7 from project start; steady-state output from Month 8.
Notes: Headline numbers use conservative biology (65% biological efficiency, 8% contamination loss, 10:1 fresh-to-dry). The notes' 80-100% BE is treated as upside, not the base case.

## Slide 3
01 · THE OPPORTUNITY
Why Lion's Mane, and why now
Lion's Mane Facility · Hamirpur, HP · Project Plan
3
Distinct bioactive profile
Fruiting bodies carry hericenones and β-glucans; erinacines sit mainly in the mycelium. Both are studied for neurotrophic (NGF-related) and cognitive-support activity. Research is ongoing, so we will make no disease claims.
Growing B2B pull
Nootropic supplements, mushroom coffee and tea, and Ayurveda-adjacent formulations are pulling demand for functional-mushroom ingredients from Indian brands.
The supply gap we target
Consistent, domestic, fruiting-body-only supply with a full certificate of analysis per lot is hard to find. Much trade material is imported or mycelium-on-grain with high starch.
Our differentiation
100% fruiting body: no grain filler, verified by starch test (<5%)
Controlled-environment grown: zero pesticides
Farm-to-dryer in under 4 hours for colour and actives
Lot-coded traceability from culture to carton
Third-party NABL CoA with every shipment
Culture sourced from ICAR-DMR Solan / accredited labs
Notes: Scientific audiences will check the chemistry: hericenones are fruiting-body compounds, erinacines are largely mycelial. Positioning as fruiting-body-only is the honest and defensible claim. Validate the supply-gap thesis with 5-10 buyer interviews before launch.

## Slide 4
01 · THE OPPORTUNITY
Why Hamirpur, Himachal Pradesh
Lion's Mane Facility · Hamirpur, HP · Project Plan
4
Genetics on the doorstep
ICAR-Directorate of Mushroom Research, Solan: the national mushroom research centre, for certified mother cultures and technical support.
Feedstock corridor
Soy hull ("soya chilka") from Punjab / Hamirpur feed mills (₹15–25/kg) and hardwood sawdust from Zirakpur sawmills (₹5/kg).
Buyer clusters in reach
Baddi–Barotiwala–Nalagarh pharma & nutraceutical belt (HP), Haridwar–Dehradun Ayurveda cluster (320 km), Delhi-NCR brands.
Hill-state incentives
Special Category State: PMEGP 35% rural subsidy with only 5% promoter contribution; MIDH/NHB horticulture support.
Favourable climate window
Cool Oct–Mar ambient suits 15–18°C fruiting and cuts HVAC load. Summers (up to ~40°C) and monsoon humidity are engineered for.
Skilled rural workforce
HP has an established mushroom-growing culture (Solan: "Mushroom City of India"), easing hiring and training.
Notes: Location advantages: genetics (ICAR-DMR Solan), feedstock (Punjab soy hull, Zirakpur sawdust), buyers (BBN cluster, Haridwar-Dehradun, NCR), incentives (special category state), and a natural cool season.

## Slide 5
02 · BIOLOGY & OUTPUT
Daily production model: substrate to powder
Lion's Mane Facility · Hamirpur, HP · Project Plan
5
155 kg
wet Master's Mix
62 kg dry · 60% moisture
60 blocks
× 2.5 kg, spawned with
6 kg grain spawn
14–21 days
dark incubation
at 21–24°C
~36 kg
fresh mushrooms
(65% BE, 8% loss)
~3.6 kg
dry powder
(10:1 fresh-to-dry)
Planning assumptions (conservative)
Biological efficiency (BE) 65% across two flushes: fresh weight ÷ dry substrate weight.
Contamination / culling loss 8% of blocks.
Fresh-to-dry ratio 10:1 (Lion's Mane is ~90% water).
26 inoculation days per month → ~93 kg dry powder per month.
Expert note on the 5 kg/day target
The notes assume 80–100% BE, which gives 4.4–5.5 kg/day from 60 blocks. That is achievable on Master's Mix with a well-adapted strain, but lenders and buyers should see a plan that works at 65%. At 65% BE, 5 kg/day needs ~90 blocks/day, so we commission at 60 in 750 sq ft and plan a later expansion to 90.
Notes: Mass balance: 31 kg hardwood + 31 kg soy hull + 93 L water = 155 kg wet at 60% moisture = 62 blocks of 2.5 kg. Each block holds ~1 kg dry substrate. At 65% BE and 8% losses, 60 blocks give ~36 kg fresh, ~3.6 kg dry.

## Slide 6
02 · BIOLOGY & OUTPUT
Yield sensitivity: what it takes to hit 5 kg/day
Lion's Mane Facility · Hamirpur, HP · Project Plan
6
Chart: Dry powder output, kg per operating day (8% loss, 10:1)
| BE 50% | BE 65% (base) | BE 80% | BE 100%
45 blocks/day (current 2-storey building) | 2.07 | 2.69 | 3.31 | 4.14
60 blocks/day (Phase 1) | 2.76 | 3.59 | 4.42 | 5.52
90 blocks/day (Phase 2) | 4.14 | 5.38 | 6.62 | 8.28
90 blocks
needed for 5+ kg/day at base 65% BE
93 → 140 kg
dry powder per month, Phase 1 → Phase 2
Every +10 points of BE adds ~0.55 kg/day at 60 blocks. Strain selection and sterilization quality are the cheapest ways to grow output.
Notes: Chart shows dry kg per operating day across block counts and BE. The base case is 65% BE. The 45-block series is what the existing 25x10 ft two-storey footprint can hold.

## Slide 7
02 · BIOLOGY & OUTPUT
Crop cycle: ~60 days from liquid culture to first harvest
Lion's Mane Facility · Hamirpur, HP · Project Plan
7
-28
-21
-14
-7
0
+7
+14
+21
+28
+35
+42
+49
Days relative to block inoculation (day 0)
Liquid culture + QC
7 d
Grain spawn run
21 d
Block incubation (dark)
21 d
Flush 1: pin → harvest
14 d
Flush 2 → block exit
14 d
Steady-state pipeline inventory (Phase 1)
~60
grain-spawn bags colonizing at any time
~1,260
blocks in incubation (60 × 21 days)
~1,500
blocks fruiting (60 × ~25 days)
35–55 kg
fresh harvest to process daily
Notes: Colonised blocks move to fruiting when fully white, before pins form inside the bag. Slit/X-cut initiates pinning in 5-7 days; first harvest ~12-14 days after the cut. Second flush is typically 30-50% of the first; blocks exit after two flushes.

## Slide 8
03 · GENETICS & SPAWN
Culture management: the strain is the business
Lion's Mane Facility · Hamirpur, HP · Project Plan
8
1
Master slant
4°C culture bank
2
P1 agar plate
clean transfer
3
Liquid culture
streak-tested 72 h
4
G1 grain spawn
mother spawn
5
G2 grain spawn
hard stop
6
Fruiting blocks
1:10 onward
Non-negotiable rules
Never expand beyond G2: each extra generation risks senescence (slow runs, weak, deformed fruit).
Every liquid-culture batch is streaked on agar and held 72 h before use; bacteria in LC are invisible.
Culture bank: 3 backup slants per strain, sub-cultured every 3–6 months; one set held off-site.
Re-isolate by tissue culture from the best fruit bodies; re-validate before commercial use.
Sourcing & strain selection
Source | Lead time | Use
ICAR-DMR, Solan (Govt.) | ~2 months, in-person pickup | Primary certified strain
Private labs (e.g., Nuvedo, BM Mushroom) | Days, courier | Backup / comparison strain
Month-5 strain trial: 2–3 strains × 30 blocks each, scored on colonization days, BE, fruit density and β-glucan. Winner becomes the production strain.
Notes: Order the ICAR-DMR culture in Month 1 because of the ~2 month lead time. Run a private-lab strain in parallel as a hedge.

## Slide 9
03 · GENETICS & SPAWN
Grain spawn SOP: daily batch for 60 blocks
Lion's Mane Facility · Hamirpur, HP · Project Plan
9
3.15 kg
dry millet / sorghum
3 L
water for soak
31.5 g
gypsum (CaSO₄), 1%
30 ml
liquid culture
6 kg
spawn = 3 × 2 kg bags
PHASE 1 · DAY 0
Hydrate
Rinse grain in cold water until it runs clear.
Cold-soak 12–16 h under 5 cm of water with the gypsum, to germinate Bacillus endospores so heat can kill them.
Simmer 15 min: chalky centre gone, hulls intact.
PHASE 2 · DAY 1
Dry, bag, sterilize
Drain; surface-dry on mesh with a fan 45–60 min. Grain must not stick to the hand.
Fill 2 kg per filter-patch bag with injection port.
121°C / 15 PSI for 120 min; let pressure fall naturally.
PHASE 3 · DAY 2
Inoculate
Cool 12 h in the positive-pressure lab to <25°C.
LAF on 30 min; wipe bags, gloves and syringe with 70% IPA.
Flame needle, cool, inject 10 ml LC per bag; seal, shake 30 s.
PHASE 4 · DAY 8–21
Break & mature
Incubate dark at 21–23°C.
At ~30% coverage (day 8–10) break and shake to redistribute.
Use when fully white (day 14–21). Discard any bag with wet, sour or discoloured patches.
Notes: Spawn rate: 6 kg per 60 blocks = 100 g per 2.5 kg block (~4% of wet weight, 10% of dry substrate). On nutrient-rich Master's Mix, raising this to 150 g per block shortens colonization and closes the contamination window; trial both in Month 5.

## Slide 10
04 · SUBSTRATE
Master's Mix: formulation, sourcing and handling
Lion's Mane Facility · Hamirpur, HP · Project Plan
10
Chart: Daily batch: 155 kg wet @ 60% moisture
| Hardwood sawdust 31 kg | Soy hull 31 kg | Water 93 L
Daily batch | 31 | 31 | 93
50 : 50 hardwood : soy hull (dry basis), hydrated to 60–62%. Squeeze test: a few drops, never a stream.
Wood selection
Approved: Mango, Poplar, Safeda/Eucalyptus, Oak
Excluded: softwoods (Pine, Deodar) and resinous or anti-fungal hardwoods (Teak, Sal, Hollock)
Suppliers (from site notes)
Input | Supplier | ₹/kg
Sawdust | Rajinder Singh & Bros, Zirakpur | 5
Soy hull | Shri Kulkanda Feeds | 20
Budget ~₹45,000/month incl. freight
Handling rules for a "hot" substrate
Master's Mix is very nutritious, so contaminants love it as much as Lion's Mane does.
Mix, bag and start sterilizing within 4 h of hydration; a wet mix left overnight sours (bacterial load rises).
Screen sawdust to 2–5 mm with some fines; avoid pure dust, which packs and goes anaerobic.
Buy hulls fresh, store dry off-site (Zone 0); reject mouldy or damp lots.
Record lot numbers of every input batch for traceability.
Notes: Recipe per notes: 31 kg hardwood + 31 kg soy hull + 93 L water = 155 kg wet, 60% moisture, ~62 blocks of 2.5 kg.

## Slide 11
04 · SUBSTRATE
Sterilization: the #1 determinant of contamination rate
Lion's Mane Facility · Hamirpur, HP · Project Plan
11
Parameter | Grain spawn | Substrate blocks
Temperature / pressure | 121°C @ 15 PSI | 121°C @ 15 PSI
Hold time at temperature | 120 min | 150–180 min (dense 2.5 kg blocks)
Load per cycle | 3 × 2 kg bags (with blocks) | 30 × 2.5 kg blocks
Cycles per day | — | 2 (Phase 1) · 3 (Phase 2)
Total cycle time | ~4.5 h | ~5.5–6 h incl. heat-up & cool-down
Cooling before inoculation | 12 h, <25°C | 12 h, <25–28°C core
Validation | BI + core thermocouple | BI in densest block, weekly
Autoclave sizing
30 blocks × ~5 L each = ~150 L of load, plus racking and steam circulation space. Specify a 400–500 L horizontal SS-304 autoclave, ideally double-door pass-through into the clean lab. A 150–200 L vertical unit cannot hold 30 blocks.
Golden rules
An interrupted cycle is a failed cycle: restart from zero, never inoculate.
Unload straight to the clean side; blocks never re-enter the dirty room.
Log time, temperature and pressure for every cycle, with lot codes.
Geobacillus stearothermophilus biological indicators weekly and after any repair.
Notes: Supplemented sawdust blocks heat slowly at the core; a 90-minute cycle that is fine for small grain bags will leave survivors in 2.5 kg Master's Mix blocks. Validate by placing a thermocouple and a biological indicator in the centre of the densest block in the coldest part of the chamber.

## Slide 12
05 · FACILITY DESIGN
Unidirectional biosecure zoning: dirty → clean → spore-wet
Lion's Mane Facility · Hamirpur, HP · Project Plan
12
ZONE 0
Bulk store
Off-site, 1 km
Isolated
ZONE 1
Prep & sterilization
Mix · bag · autoclave
Negative
ZONE 2
Anteroom + clean lab
Gown · cool · inoculate
Positive ++
ZONE 3
Incubation
Dark · 21–24°C
Neutral
ZONE 4
Fruiting A / B
Spore-wet · 85–95% RH
Negative
ZONE 5
Processing & pack
Dry · mill · pack
Positive, dry
Transfer points: sealed bags by van (0→1) · double-door autoclave or UV SS-304 pass box (1→2) · pass-through hatch (2→3) · stairs/lift, closed crates (3→4) · harvest crates via dedicated door (4→5)
Material flow
Forward only. Nothing returns upstream. Spent and contaminated blocks exit Zone 4 by the back door, never through clean zones.
People flow
Clean → dirty within a day. The lab technician inoculates first, freshly gowned, and never enters fruiting or prep before sterile work.
Air flow
Pressure cascades from clean to dirty: clean lab +10–15 Pa over anteroom; prep and fruiting exhaust outdoors so spores leave the building.
Notes: The facility is designed so that material moves only forward, people move from clean to dirty, and air pressure cascades from clean to dirty. This is the single most important design decision for contamination control.

## Slide 13
05 · FACILITY DESIGN
Room-by-room environmental specification
Lion's Mane Facility · Hamirpur, HP · Project Plan
13
Zone | Temp | RH | CO₂ | Light | Pressure & air | Key equipment
1 · Prep & sterilization | Ambient | Ambient (steam) | — | Work light | Negative; louvre exhaust outdoors | 200 L ribbon mixer, bag filler, impulse sealer (≥5 mm seal), 400–500 L autoclave
2 · Anteroom + clean lab | 20–22°C | 45–50% | — | Work light; UV-C when empty | +10–15 Pa vs anteroom; H14 HEPA intake; ISO 5 at hood, ISO 7/8 room | 2 × LAF hoods (H14, ~0.45 m/s), SS cooling racks, sealer, UV pass box
3 · Incubation | 21–24°C air; core <27°C | 60–70% | >2,000 ppm is fine | Dark | Neutral; recirculation fans | 9-ft epoxy racks, core-temp probes, T/CO₂ controller, inverter AC
4 · Fruiting A / B | 15–18°C (max 20°C) | 85–95% | <800 ppm | 12 h, 500–1,000 lux, 6500 K | Negative; MERV 13 intake high, exhaust 6" off floor; 6–8 ACH | 10-head ultrasonic humidifier + humidistat, CO₂-controlled FAE fans, waterproof LED
5 · Processing & pack | <25°C | <40% | — | Normal | Slight positive; dehumidified | Slicer, 96-tray dehydrator (45–50°C), 3 HP pulverizer, sifter, vacuum sealer
Reconciled from site notes: incubation air is held at 21–24°C (setpoint 22°C) because Lion's Mane blocks run 3–5°C hotter at the core through thermogenesis.
Notes: The notes gave slightly different incubation temperatures (21-24, 23-24, 22). We control air at 22 C so block cores stay below 27 C.

## Slide 14
05 · FACILITY DESIGN
Clean-room civil & HVAC engineering
Lion's Mane Facility · Hamirpur, HP · Project Plan
14
Element | Specification
Walls & ceiling | 50–80 mm PUF sandwich panels, 40 kg/m³, PPGI finish, RTV silicone joints
Floor | 2–3 mm seamless epoxy resin; no tiles or grout lines
Corners | 50R–75R extruded aluminium coving; no 90° dead zones
Airlock | Two-door interlocked anteroom for gowning; door closers
Transfer | Double-door autoclave or SS-304 UV pass box with interlock
Fixtures | Flush sealed LED; SS-304 tables; no wood or bare steel
Pressure cascade
Outdoors
0 Pa
Anteroom
+5–10 Pa
Clean lab
+15–25 Pa
LAF zone
ISO 5
Air always leaks from clean to dirty, never the reverse.
Hybrid start-up HVAC
Inverter split ACs for cooling: copper coils only, as humidity and spores corrode aluminium fins.
Inline centrifugal blower → G4 pre-filter → MERV 13 → H14 HEPA terminal box pressurizes the lab.
Gravity relief dampers bleed excess air to the anteroom to hold the differential.
Magnehelic gauge at each door, logged twice daily; PAO HEPA-integrity test at commissioning, then annually.
Notes: This hybrid model (commercial split ACs plus a HEPA-filtered make-up air box) is far cheaper than a full AHU cleanroom and is adequate for mushroom inoculation when combined with ISO 5 laminar flow hoods.

## Slide 15
05 · FACILITY DESIGN
Incubation room: 1,260 blocks in the dark, heat under control
Lion's Mane Facility · Hamirpur, HP · Project Plan
15
R1
R2
R3
R4
R5
R6
R7
R8
5 ft working aisle
Hatch
from lab
Plan view · 16 × 10 ft (160 sq ft) · 8 racks, door on the short wall
Each rack: 4 ft × 2 ft × 9 ft, 8 tiers × ~20 blocks = ~160 blocks → 8 racks ≈ 1,280 blocks. Grain-spawn bags colonize on a wire shelf in the clean lab.
Manage thermogenesis
Colonizing mycelium generates its own heat. Hold air at 22°C; probe 5 block cores per rack daily and act above 27°C. Leave 2–3 cm between blocks and run ceiling circulation fans.
Minimal fresh air
High CO₂ (>2,000 ppm) actually favours vegetative growth. Only enough exchange for worker safety; no misting; RH 60–70%.
Exit criteria
Move to fruiting at full colonization (14–21 days) or when pins start inside the bag, whichever is first. Trapped pins deform.
Notes: 60 blocks per day x 21 days = 1,260 blocks. Racks are 4 ft wide by 2 ft deep, 9 ft tall with 8 tiers. Incubation packing density is much higher than fruiting because no fruit bodies need space yet.

## Slide 16
05 · FACILITY DESIGN
Fruiting rooms: space for fruit bodies, air for pom-poms
Lion's Mane Facility · Hamirpur, HP · Project Plan
16
6"
Row A · 24" racks
24"
36" harvest aisle
24" cart
36"
Row B · 24" racks
24"
6"
Cross-section: 96" minimum clear width (10 ft room gives extra wall clearance)
Lowest tier 6–8" off the floor, where CO₂ pools. Tier pitch 16–18" so fruit bodies never touch the shelf above.
Capacity check
Per rack: 6 tiers × ~16 blocks (3–4" apart) = ~96 blocks
Per 16 × 10 ft room: 2 rows × 4 racks = ~770 blocks
Rooms A + B = ~1,540 blocks ≥ 1,500 needed (60/day × 25 days)
Site-note density of 30 blocks per shelf is too tight for Lion's Mane
Fresh-air exchange
Keep CO₂ <800 ppm; above ~1,000 ppm spines elongate into coral shapes. Intake high through MERV 13 + mist, exhaust 6" off floor, 6–8 ACH on a CO₂ controller, 40-mesh insect screens.
Humidity without wetting
85–95% RH from a 10–12 head ultrasonic fogger on a humidistat, fed with RO water. Droplets on the fruit cause yellowing and bacterial blotch; fog the air, never the mushroom.
Light & initiation
12 h/day at 500–1,000 lux (6500 K waterproof LED). X-cut or 3–4 cm slit facing the aisle. Harvest at 0.5–1 cm spines, still white. Run A/B all-in, all-out for deep cleans.
Notes: Two smaller fruiting rooms beat one large one: you can empty, clean and sanitize one while the other produces, which breaks pest and mould cycles.

## Slide 17
06 · EXPERT DESIGN REVIEW
Corrections applied to the site notes before build
Lion's Mane Facility · Hamirpur, HP · Project Plan
17
# | Item | In the notes | Recommendation | Why it matters
1 | Biological efficiency | 80–100% | Plan at 65%; treat 80%+ as upside | Second flush is weak; lenders need a conservative base
2 | Autoclave size | 150–200 L vertical, 30 bags/cycle | 400–500 L horizontal, double-door | 30 × 2.5 kg blocks do not physically fit 200 L
3 | Block sterilization | 90–120 min | 150–180 min hold, BI-validated | Dense supplemented blocks heat slowly at the core
4 | Prep room size | 6 × 10 ft (60 sq ft) | 90 sq ft + covered outdoor mixing shed | 155 kg/day mixing, bagging, drainage, washing
5 | Fruiting density | 30 blocks/shelf, one 250 sq ft room | ~16 blocks/shelf, two 160 sq ft rooms | Fruit bodies need space; A/B allows sanitation
6 | Power budget | 140–160 kWh/day | 200–250 kWh/day (summer) | Autoclave + cooling vs. 40°C summers + block heat
7 | DG set | 15–20 kVA for all loads | 20 kVA for life-support; autoclave on grid | Autoclave heaters alone can exceed 20 kVA
8 | Health messaging | "Cold use blocks absorption" | Usage guidance only, no disease claims | FSSAI restricts claims; scientists will challenge
These are the points a technical reviewer or lender is most likely to challenge; the rest of this plan already reflects them.
Notes: Walk through each correction. The biggest are autoclave sizing and sterilization time (contamination), fruiting density and room count (quality), and yield assumptions (finance).

## Slide 18
06 · EXPERT DESIGN REVIEW
Space validation: the building must match the biology
Lion's Mane Facility · Hamirpur, HP · Project Plan
18
Zone (sq ft) | Current 2-storey | Phase 1 · 750 sq ft | Phase 2 · 90/day
0 · Bulk store | Off-site (1 km) | Off-site (1 km) | Off-site (1 km)
1 · Prep & sterilization | 60 | 90 + outdoor mixing shed | 120
2 · Anteroom + clean lab | 60 | 70 (20 + 50) | 80
3 · Incubation | 130 | 160 (16 × 10) | 240
4 · Fruiting rooms | 250 (1 room) | 320 (2 × 16 × 10) | 480 (3 × 16 × 10)
5 · Processing & packing | — | 90 | 120
QC · office · FG store | — | 20 | 40
On-site total | ~500 | 750 | ~1,080
Blocks per day | ~45 | ~60 (at limit) | 90
Dry output, base case | ~2.7 kg/day | ~3.6 kg/day | ~5.4 kg/day
Finding
750 sq ft carries Phase 1 at ~60 blocks/day (~93 kg/month) only with every zone racked to the limits shown. 150 kg/month in this footprint needs ~100% BE; at base BE it needs ~1,080 sq ft.
Recommendation
Mix substrate in a covered outdoor shed, incubate spawn in the clean lab, and run fruiting rooms A/B at full rack height. Reserve adjacent land or a floor for the Phase 2 extension.
Notes: Current: substrate 6x10, clean lab 6x10, incubation 13x10, fruiting 25x10. Phase 1 is fitted into 750 sq ft on site plus off-site storage; incubation and fruiting space set the ~60 blocks/day ceiling.

## Slide 19
07 · PROCESSING
Post-harvest: from fresh fruit body to stable powder in 24 hours
Lion's Mane Facility · Hamirpur, HP · Project Plan
19
1
Harvest
Spines 0.5–1 cm, white; cut at base with a clean knife
2
Hold
<4 h in single-layer vented crates; 2–4°C if delayed
3
Slice
8–10 mm on electric slicer for even drying
4
Dehydrate
45–50°C for 10–16 h to protect heat-labile actives
5
Verify
Moisture ≤8%, aw ≤0.60; pieces snap cleanly
6
Mill & sieve
3 HP pulverizer; 80–100 mesh; magnet trap
7
Pack & code
<40% RH room; foil + desiccant; lot code
Dryer sized to the harvest
A 96-tray dehydrator takes ~50–55 kg fresh per overnight run, matching Phase 1 peak harvest. Phase 2 adds a second unit.
B2B packing spec
5 kg triple-laminate aluminium foil bags with desiccant, heat-sealed (vacuum or N₂ flush), 4 per HDPE drum. Shelf life 12–24 months.
Monsoon defence
Powder is hygroscopic and clumps within minutes in monsoon air. A commercial dehumidifier holds the mill and pack room below 40% RH.
Notes: Lion's Mane bruises and yellows quickly. Handle by the base, never squeeze the spines, and get it into the dryer the same day. For B2C packs, advise use in hot preparations (tea, coffee, cooking); heat helps release beta-glucans from chitin cell walls. This is usage guidance, not a health claim.

## Slide 20
08 · QUALITY & COMPLIANCE
Quality control: a CoA with every lot, controls at every step
Lion's Mane Facility · Hamirpur, HP · Project Plan
20
Parameter | Method | Specification
Identity | Macroscopy; ITS DNA barcode (per strain); HPTLC | H. erinaceus fruiting body
Moisture / water activity | Loss on drying / aw meter | ≤ 8% / ≤ 0.60
β-glucans | Megazyme K-YBGL | Report; target ≥ 20%
α-glucan (starch) | Megazyme enzymatic | < 5%: proves no grain filler
Particle size | Sieve analysis | 80–100 mesh
Heavy metals (Pb, Cd, As, Hg) | ICP-MS, NABL lab | Within FSSAI contaminant limits
Microbiology | TPC, yeast & mould, E. coli, Salmonella, S. aureus | Within FSSAI / buyer limits
Pesticide residues | LC-MS/MS, GC-MS/MS | Within FSSAI MRLs (none applied)
In-process controls
Biological indicator in every weekly autoclave validation run.
LAF settle plates weekly; particle count monthly.
Contamination log per lot; targets <5% blocks, <2% spawn.
Continuous T / RH / CO₂ data logging in every room.
Lot code LM-YYMMDD-Room-Rack traces culture batch to dispatch.
Retained sample from every lot, kept 24 months.
Notes: The starch test is the single most powerful commercial differentiator: mycelium-on-grain products typically show high starch and low beta-glucan. Quote beta-glucan and starch on every CoA.

## Slide 21
09 · PRODUCTS & MARKET
Value-addition roadmap: earn the right to each step
Lion's Mane Facility · Hamirpur, HP · Project Plan
21
PHASE 1 · MONTH 7–18
Bulk ingredient
Fruiting-body powder, 80–100 mesh, 5 kg drums
Dried slices for extractors
Fresh surplus to local HoReCa
Needs: FSSAI licence · included in Phase-1 capex
PHASE 2 · YEAR 2
Brand & private label
B2C 100 g pouches with hot-use instructions
Mushroom coffee / tea blends
Private label for D2C brands
Needs: Legal Metrology (LMPC), trademark, pouch filler
PHASE 3 · YEAR 3+
Extracts
Hot-water extract: vacuum evaporation + spray drying, standardized β-glucan
Dual-extract tinctures: 70–95% ethanol + 80–90°C decoction, final >25% ABV
Needs: extraction capex, HP Excise licence (ENA), fire upgrade
Realized price per kg rises at each step, but so do capex, licensing and working capital. Each phase is funded by the one before it.
Notes: Erinacines concentrate in mycelium, so a future mycelial or ethanol-extract line is a scientifically distinct product, not a substitute for fruiting-body powder.

## Slide 22
09 · PRODUCTS & MARKET
Target buyers and what each one needs from us
Lion's Mane Facility · Hamirpur, HP · Project Plan
22
Nutraceutical brands
Capsules, gummies, powders
Needs: CoA every lot, fixed mesh, fruiting-body declaration, annual contracts
Ayurveda manufacturers
BBN (HP) · Haridwar–Dehradun
Needs: Botanical identity, heavy metals, bulk drums, stable pricing
Nootropic & mushroom-coffee D2C
Delhi-NCR, Mumbai, Bengaluru
Needs: Small MOQs (25–100 kg), fast samples, private label
B2B extractors
Make 10:1 and β-glucan extracts
Needs: Dried slices or whole, low moisture, volume and price
Surplus valve: fresh Lion's Mane to premium restaurants and hotels in Chandigarh, Shimla and Dharamshala absorbs flush peaks without discounting powder.
Notes: Validate each segment with 2-3 buyer conversations and sample requests before Month 6.

## Slide 23
09 · PRODUCTS & MARKET
Pricing ladder and B2B qualification path
Lion's Mane Facility · Hamirpur, HP · Project Plan
23
₹ per kg, dry
Cash cost
~₹3,000
B2B bulk powder
₹8,000–12,000
B2C retail (100 g)
₹18,000–25,000+
At ₹8,000/kg the gross margin over cash cost is ~63%. B2C multiplies price per kg by ~2.5×, but adds packaging, marketing and retailer margins, so it is phased in during Year 2.
B2B qualification (3–6 months)
1. Sample kit
50–100 g + CoA from pilot lots
2. Buyer lab test
Identity, β-glucan, contaminants
3. Vendor audit
Site visit, SOPs, traceability
4. Trial PO
25–100 kg first order
5. Supply agreement
Annual volume, price band, quarterly calls
Notes: Start sampling from pilot production in Month 5-6 so buyer qualification runs in parallel with the ramp. Expect 30-90 day credit terms; an early-payment discount of ~2% can pull cash forward.

## Slide 24
09 · PRODUCTS & MARKET
Distribution and logistics: dry product, simple chain
Lion's Mane Facility · Hamirpur, HP · Project Plan
24
Lane | Mode | Indicative freight
Hamirpur → Dehradun (320 km) | LTL: Safexpress / Delhivery | ₹15–30 per kg
Hamirpur → BBN cluster, HP | LTL or shared dedicated | ₹15–30 per kg (to confirm)
Hamirpur → Delhi-NCR | LTL / express surface | ₹15–30 per kg (to confirm)
Samples & small MOQs | Courier | Per parcel
Fresh to HoReCa | Insulated boxes, 2–4°C | Within 48 h of harvest
Dry powder needs no cold chain. At ₹25/kg freight on ₹8,000/kg product, logistics is ~0.3% of revenue, so distance from Delhi is not a competitive handicap.
Every dispatch carries
GST tax invoice
E-way bill (goods value > ₹50,000)
Lot-wise CoA, lot code on each drum
Transit insurance at 0.5–1% of value
Moisture-proof foil + desiccant packing
Packing list with net / gross weights
Notes: Freight rates beyond Dehradun are planning estimates based on the Dehradun quote; confirm with carriers.

## Slide 25
10 · ECONOMICS
Capital expenditure: Phase 1, right-sized (₹ lakh)
Lion's Mane Facility · Hamirpur, HP · Project Plan
25
Item | ₹ L
Civil works, PUF clean-room panels, epoxy floor, coving, doors | 2.20
Autoclave: 2 × 150 L vertical, SS-304 | 1.10
Processing: slicer, 96-tray dehydrator, 3 HP pulverizer, sifter, vacuum sealer, dehumidifier | 2.40
HVAC: copper-coil inverter ACs, H14 HEPA box, FAE fans, ducting | 1.40
DG set 10–12.5 kVA with auto-transfer switch | 1.60
Epoxy-coated racking: incubation + two fruiting rooms | 0.55
Mixer 200 L, bag filler, impulse sealers, cooling racks | 0.70
Electrical, plumbing, drainage, RO water | 0.80
1 × LAF hood, UV pass box, airlock | 0.70
Humidifiers, humidistats, T / RH / CO₂ controllers and loggers | 0.55
Culture & spawn lab: grain kettle, fridge, agar kit, incubator | 0.60
QC lab: moisture analyser, microscope, balances | 0.45
DPR, licences, validation, certifications | 0.45
Subtotal | 13.50
Contingency (10%) | 1.35
Working capital (3 months OpEx + receivables buffer) | 4.00
Total project cost | 18.85
₹14.85 L
Fixed capital incl. contingency
Total project cost is fully eligible for the MSME PMEGP 35% Rural Subsidy.
Figures are planning estimates. Firm them with 3 vendor proforma invoices per item, which the MIDH/NHB route also requires.
Notes: Right-sized budget targeting 150 kg/month, kept under the Rs 50 L PMEGP project-cost cap. Rent and land excluded (own premises assumed). Microscope (contamination ID) and RO water (clean humidifier feed, no scale) are retained as essential.

## Slide 26
10 · ECONOMICS
Operating costs: Phase 1 steady state (₹ per month)
Lion's Mane Facility · Hamirpur, HP · Project Plan
26
Cost head | ₹ / month
Labour (5 staff) | 99,000
Power (~220 kWh/day at ~₹7) | 46,000
Substrate: sawdust + soy hull incl. freight | 45,000
Filter-patch bags (blocks + spawn) | 17,000
NABL testing (lot CoAs) | 15,000
Lab consumables: IPA, gloves, masks, pre-filters | 12,000
Maintenance & miscellaneous | 12,000
Packaging | 10,000
Diesel for DG backup | 8,000
Grain, gypsum, culture media | 6,000
Logistics & insurance | 6,000
Total | 2,76,000
₹2,960
cash cost per kg dry powder
35 kg
monthly break-even at ₹8,000/kg (37% of capacity)
Power budget, kWh/day (summer peak)
Cooling (4–5 ACs, ~7 TR)
125
Autoclave, 2 cycles
50
Dehydrator
35
Fans, LAF, fogger, lights, mill
15
Total ~225 kWh/day in summer, ~150 in winter. Rooftop solar is a Year-2 option.
Notes: Labour: production manager/mycologist Rs 35k, lab technician Rs 22k, three associates at Rs 14k each. Rent excluded.

## Slide 27
10 · ECONOMICS
Three-year projection (₹ lakh, pre-tax, pre-debt service)
Lion's Mane Facility · Hamirpur, HP · Project Plan
27
Chart: 
| Year 1 | Year 2 | Year 3 (Phase 2)
Revenue | 38.8 | 89.6 | 134.3
Operating cost | 22.8 | 33.1 | 46.8
EBITDA | 16 | 56.4 | 87.5
Y1: sales from Month 7 (485 kg). Y2: full Phase 1 (1,120 kg). Y3: Phase 2 at 90 blocks/day (1,680 kg) after added Phase 2 capex. Price flat at ₹8,000/kg; no extract upside modelled.
Monthly EBITDA sensitivity, Phase 1 (₹ lakh)
Price / BE | 50% | 65% | 80%
₹6,000/kg | 1.55 | 2.84 | 4.13
₹8,000/kg | 2.98 | 4.70 | 6.43
₹10,000/kg | 4.42 | 6.57 | 8.72
~13 mo
EBITDA payback on ₹18.85 L from project start
+₹1.5 L
monthly EBITDA even at worst case (₹6,000, 50% BE)
The plant stays cash-positive across every price and yield combination tested.
Notes: Payback: Year 1 EBITDA of Rs 16 L plus about Rs 4.7 L in Month 13 recovers the Rs 18.85 L project cost at roughly month 13. Debt service and tax are not included; the bank DPR will add these.

## Slide 28
10 · ECONOMICS
Funding structure and government support
Lion's Mane Facility · Hamirpur, HP · Project Plan
28
PMEGP (MSME / KVIC)
Recommended lead route
35% margin-money subsidy for rural units in a Special Category State; 5% promoter contribution. Manufacturing project cap ₹50 L.
MIDH / NHB
Alternate for larger scope
Credit-linked back-ended subsidy on eligible horticulture infrastructure (50% in HP per notes). DPR with 3 proformas; no purchases before in-principle approval.
PMFME (MoFPI)
For processing assets
35% credit-linked subsidy up to ₹10 L on food-processing machinery (dryer, mill, packing).
AIF
Interest cost reducer
3% interest subvention on eligible term loans; can sit alongside a capital subsidy.
Indicative sources of funds (₹ L)
Source | ₹ L
Promoter contribution (5%) | 0.94
PMEGP bank term loan (95%) | 17.91
Margin-money subsidy (35%, adjusted after lock-in) | (6.60)
Total project cost | 18.85
The whole ₹18.85 L project sits under the ₹50 L PMEGP cap. The ~₹6.6 L subsidy is held and adjusted against the loan after a 3-year lock-in. Capital subsidies generally cannot be claimed twice on one asset: confirm the route per asset with DIC Hamirpur, KVIB, HP Horticulture and NHB.
Notes: Scheme parameters change; verify current guidelines and cost norms at the DPR stage. Not financial or legal advice.

## Slide 29
11 · REGULATORY
Licensing roadmap
Lion's Mane Facility · Hamirpur, HP · Project Plan
29
Licence / registration | Authority | When | Note
Udyam (MSME) | Ministry of MSME portal | M1 | Free; prerequisite for schemes
GST registration | GSTN | M1 | B2B invoicing and e-way bills
Trade licence / panchayat NOC | Local body | M1–M2 | Premises use
HP Horticulture registration | Dept. of Horticulture, HP | M1–M2 | Needed for the MIDH/NHB route
Consent to Establish → Operate | HP State Pollution Control Board | M2 → M4 | White category per notes; confirm
Fire NOC | HP Fire Services | M4 | Autoclave, IPA store, DG, electricals
FSSAI licence | FSSAI (State or Central) | M4, before sale | Category depends on product; confirm H. erinaceus status for health-supplement use
Legal Metrology (LMPC) | Legal Metrology, HP | Phase 2 | Mandatory for B2C pre-packs
Trademark | IP India | Phase 2 | Protect the brand before B2C launch
State Excise (ENA) | HP Excise Dept. | Phase 3 | Only for ethanol tinctures
Claims discipline
FSSAI does not permit disease-treatment claims on foods or health supplements. Labels and buyer decks will describe composition (β-glucan, fruiting body) and usage only.
If Hericium erinaceus is not listed in the applicable FSSAI schedule for the intended use, the non-specified food approval route applies.
Notes: Confirm FSSAI category and licence tier with a food regulatory consultant before Month 4. Not legal advice.

## Slide 30
12 · OPERATIONS
Team and daily operating rhythm
Lion's Mane Facility · Hamirpur, HP · Project Plan
30
Promoter / Facility Head
Sales, finance, compliance
Production Manager–Mycologist
Strains, SOPs, QC release
Lab Technician
Culture, spawn, inoculation
Production ×2
Substrate & autoclave; fruiting & harvest
Processing
Dry, mill, pack, dispatch
5 staff plus promoter; Phase 2 adds one production associate. Training at ICAR-DMR Solan before commissioning.
A day in the plant
06:30
Lab tech gowns in; LAF runs 30 min; UV off
07:00
Inoculate yesterday's cooled blocks (60) and spawn bags
08:00
Mix and bag batch 1; autoclave cycle 1 starts
10:00
Fruiting rooms: harvest, CO₂/RH checks, remove spent blocks
12:00
Slice harvest and load dehydrator
14:00
Mix batch 2; autoclave cycle 2; unload cycle 1 to clean side
16:00
Mill and pack yesterday's dry lot; lot coding
17:30
Sanitation clean → dirty; logs signed off
Notes: Personnel move clean to dirty within a day. The lab technician does sterile work first and never enters fruiting or prep beforehand.

## Slide 31
13 · IMPLEMENTATION
Nine months from approval to steady state
Lion's Mane Facility · Hamirpur, HP · Project Plan
31
M1
M2
M3
M4
M5
M6
M7
M8
M9
DPR, bank and subsidy applications
Order mother culture (ICAR-DMR) + backup
Udyam, GST, Horticulture, HPSPCB CTE
In-principle subsidy approval (pre-purchase)
Civil and clean-room build
Equipment procurement and installation
FSSAI, Fire NOC, HPSPCB CTO
Commissioning and validation (BI, HEPA, ΔP)
Strain trial and pilot blocks
Commercial ramp 30 → 60 blocks/day
First harvest, drying, NABL CoA
Buyer sampling → trial POs
Steady-state operations
◆ Milestones: first harvest M7 · steady state M8
Notes: Critical path: subsidy in-principle approval gates equipment purchase; culture lead time gates the strain trial. Start both in Month 1.

## Slide 32
14 · RISK
Risk register and mitigation
Lion's Mane Facility · Hamirpur, HP · Project Plan
32
Risk | L | I | Mitigation
Trichoderma (green mould) in blocks | M | H | Validated sterilization, HEPA, unidirectional flow; remove infected bags unopened via back door
Bacillus / wet spot in grain spawn | M | M | 12–16 h soak, full surface drying, 120 min cycles, LC streak test
Power outages (monsoon) | H | H | 20 kVA DG for HVAC, FAE, LAF; interrupted autoclave cycles fully re-run
Summer heat + thermogenesis | H | M | PUF insulation, sized copper-coil ACs, daily core-temp checks
Poor fruit quality (coral, yellowing) | M | M | CO₂ <800 ppm, fog not droplets, harvest at 0.5–1 cm spines
Sciarid / phorid flies | M | M | 40-mesh screens, sticky traps, A/B all-in all-out; no pesticides
Strain senescence | L | H | G2 cap, culture bank with off-site backup, annual re-validation
Powder clumping in monsoon | H | M | Pack room <40% RH, foil + desiccant, aw ≤0.60 release test
Autoclave breakdown (single point) | M | H | AMC and spares kit; second autoclave in Phase 2
B2B payment delays / demand dip | M | H | ₹4 L WC buffer, 12–24 mo shelf life, B2C and fresh channels, oyster/shiitake pivot
Regulatory or claims non-compliance | L | H | Pre-cleared labels, CoA per lot, regulatory consultant
L = likelihood, I = impact · H high · M medium · L low
Notes: The biggest operational risks are contamination and power. Both are addressed in design (sterilization validation, pressure cascade, DG) rather than left to operators.

## Slide 33
14 · GOVERNANCE
KPIs we will report monthly
Lion's Mane Facility · Hamirpur, HP · Project Plan
33
<5%
block contamination rate
<2%
spawn contamination rate
≥65%
biological efficiency (stretch 80%)
≤21 d
block colonization time
9–11 : 1
fresh-to-dry ratio
≤₹3,000
cash cost per kg dry
100%
lots passing CoA first time
≥95%
on-time B2B deliveries
Weekly production review on lot data; monthly dashboard to promoters, lenders and scientific advisors. Any contamination spike above 8% triggers a root-cause review of sterilization and pressure logs within 48 h.
Notes: Every KPI is measurable from the lot logs, data loggers and CoAs described earlier.

## Slide 34
15 · SUSTAINABILITY & SAFETY
A circular, safe workplace
Lion's Mane Facility · Hamirpur, HP · Project Plan
34
Circular operations
Spent substrate (~100–120 kg/day) goes to vermicompost and mulch for local farmers and nurseries: a small revenue line and a clean HPSPCB story.
Inputs are agro-industrial by-products: sawmill dust and soy hulls.
Water: ~95 L/day into substrate plus cleaning; RO reject reused for floor washing.
No pesticides or fungicides, ever; buyers test for residues.
Rooftop solar (20–30 kWp) evaluated in Year 2 to offset daytime cooling.
Worker safety
N95 / FFP2 masks in fruiting rooms: repeated spore exposure can cause hypersensitivity pneumonitis ("mushroom worker's lung").
Autoclave: trained operators only, safety-valve tests, heat-resistant gloves, never open under pressure.
IPA is flammable: small dispensed volumes; flame only after alcohol has evaporated; CO₂ extinguisher in lab.
Slip-resistant epoxy in wet rooms; trolleys for loads over 20 kg.
First-aid kit and trained first-aider on every shift.
Notes: Spore allergy is the most under-appreciated occupational risk in mushroom farming. Masks in fruiting rooms are mandatory.

## Slide 35
DECISIONS REQUESTED
Next steps to start the plant
1
Approve the phased plan
Phase 1 at 60 blocks/day with a right-sized ₹18.85 L budget, within the PMEGP cap.
2
Lock the 750 sq ft layout
Rack every zone to plan, add a covered outdoor mixing shed, and reserve space for Phase 2.
3
Launch DPR and subsidy route
PMEGP-led application with DIC Hamirpur; collect 3 proformas per major item.
4
Place the culture order now
ICAR-DMR Solan has a ~2-month lead time; add a private-lab backup strain.
5
Open buyer conversations
Line up 5–10 B2B buyers for pilot samples from Month 5.
Notes: Close by asking for the five decisions. The two long-lead items, culture and subsidy approval, should start this month.